## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Teta Butera Nelly | Database & Backend Lead | t.nelly@gmail.com
Murenzi Bonheur | Data Processing & Algorithm Lead | m.bonheur@gmail.com
Melyssa Ingabe Mbayire | Frontend & Visualization Lead | m.mbayire@gmail.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Dataset exploration & database design | Nelly | 13th Feb | Completed | Yes
| data cleaning | Bonheur | 14th Feb | Completed | Yes
| Backend API development | Nelly | 15th Feb | Completed | Yes
| Frontend dashboard | Melyssa | 17th Feb | Completed | Yes
| System architecture diagram | Melyssa | 17th Feb | Completed | Yes
| Technical documentation report | Bonheur | 18th Feb | Completed | Yes
| README file | All | 18th Feb | Completed | Yes
| Final testing and bug fixes | All | 18th Feb | Completed | Yes
| Video walkthrough recording | All | 18th Feb | Completed | Yes
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
13th Feb | Project kickoff and requirements review Initial dataset exploration Task allocation and role assignment Database design discussion Timeline planning | Nelly | All | Reviewed assignment requirements and downloaded all three datasets, identified data quality issues including missing LocationIDs, assigned roles, agreed on tools, and set up GitHub repository. | Nelly: Design database schema with normalized tables by 14th Feb Bonheur: Start data cleaning scripts by 14th Feb Melyssa: Research visualization libraries and create wireframes for dashboard All: Review each other's work on GitHub before next meeting Next meeting: 15th Feb at 4:00 PM
15th Feb | Database schema review and approval Data cleaning progress check Backend API endpoint planning Feature engineering discussion Frontend design review | Bonheur | All | Approved database schema, Bonheur demonstrated data cleaning, planned 3 derived features: trip efficiency, peak hour indicator, borough flow patterns. Defined 5 REST API endpoints. Melyssa presented dashboard wireframes. Decided on custom merge sort algorithm for zone ranking. | Nelly: Complete backend API development by 15th Feb Bonheur: Finish feature engineering and implement custom sorting algorithm by 17th Feb Melyssa: Build dashboard UI structure and integrate Chart.js by 17th Feb All: Begin drafting individual documentation sections Next meeting: 17th Feb at 2:00 PM
17th Feb | System integration testing Frontend-backend connection verification Custom algorithm review and complexity analysis Visualization strategy finalization Architecture diagram creation | Melyssa | All | Successfully tested complete data flow from raw data to frontend. All API endpoints verified with proper JSON responses. Bonheur presented merge sort algorithm with complexity analysis (O(n log n) time, O(n) space), confirmed no built-in libraries used. Melyssa demonstrated working dashboard with 5 chart types and interactive map showing 263 taxi zones. Created AWS-style architecture diagram. Fixed minor bugs in date picker and map zoom. | Nelly: Write README file with installation instructions and environment setup by 18th Feb Bonheur: Complete technical documentation section on algorithm and data structures by 18th Feb Melyssa: Polish frontend UI, add loading animations and error messages All: Finalize individual documentation sections Next meeting: 18th Feb at 1:00 PM for final review
18th Feb | Final system testing and bug fixes Documentation compilation and review Video walkthrough script preparation README verification Submission checklist review | Nelly | All | Conducted end-to-end testing - all components working correctly. Reviewed complete technical documentation (2.5 pages) with all required sections. Verified README instructions on fresh environment. Prepared 5-minute video script with assigned sections: Nelly (intro/architecture), Bonheur (algorithm/insights), Melyssa (frontend demo). Completed submission checklist: codebase ZIP, GitHub link, documentation PDF, video link, team sheet all ready. Scheduled video recording for 6:00 PM. | All: Record video walkthrough at 6:00 PM today (18th Feb) Nelly: Upload video to YouTube/Google Drive and add link to README Bonheur: Create final ZIP file with all code and documentation Melyssa: Final proofreading of documentation PDF All: Submit complete package by 11:59 PM tonight Follow-up: Ensure all team members can individually explain the project for random calls